## stories
STORY ID | Story | Description
1 | SPIKE: List of all atomic validators | Atomic validators are validators that cannot be broken down any further but for regular expressions. Ex: Person's Name. Full name would be a combination of two names(Fname/Lname)
2 | SPIKE: List of all combinatoral validators | Validators that are finally applied to fields (in the excel sheet). Phone numbers, Names etc; are all combinatoral validators
3 | Validators for individual worksheets/forms | A collection of validators that can be need to be applied to worksheets
4 | Ability to turn on and turn off validators/field | All fields by default will have validators turned on. However fields should have the ability to have the validators turned off on them
5 | Website link mapping with SiteID and EmailID | Mapping with siteID and EmailID for Download Link and Upload
6 | Expire site on the basis of Siteid | DocuTAp representative can expire siteid on the basis of requirement,Once a clinic representative uploads a Clinic details file as an XLS file verify that it is a file that is a valid input for the Data Uploader application
7 | Excel Upload for DocuTAP representative | DocuTAp representative can upload excel file and validate,Once a clinic representative uploads a Clinic details file as an XLS file verify that it is a file that is a valid input for the Data Uploader application
8 | SPIKE : Disable macro and copy macro from another sheet and paste it. | Disable and enable macro from excel sheet
9 | Error handling: Show the proper message during the process | Exception handling during uploading.
10 | Excel Upload for Clinic representative | Clinic representative will upload excel file and validate the file after validate the file should mapped with siteid and go for forther process.
11 | Website link generation for download DocuTAP implementation team | DocuTAP's clinic implementation team should be able to generate a single use link
12 | Notification for state changes | Whenever the Clinic details file has a state change, notify both the parties (DocuTAP and Clinic reps) by email
13 | One time link (OTL) for providing Clinic template | This link generates a link that provides the Clinic representative with a downloadable Excel file (template)
14 | Webservice for copying/stream/feeding documents from disc/DFS/NAS | The website should invoke a webservice to upload or fetch documents from disc. The file location will be behind a firewall hence not directly accessible to the Webserver. The webservice needs to be setup to have permissions to access files on the disc.
15 | Filenaming convention | Come up with a filename convention to avoid conflicts. Suggested parameters: Clinic name, date of transaction, GUID
16 | SPIKE: Auto fill details fields | Figure out all the fields in each form that can be automatically filled in
17 | Store details for Clinic and DocuTAP reps/Clinic | The two responsible parties for implementaion are DocuTAP representative and a Clinic representative. We need to map these details server side.
18 | Generate unique tracking number for each Clinic | Unique ID for each Clinic should be embedded and validated in the Excel file that goes out
19 | Enforce HTTPS | The website should support HTTPS and HTTPS only
20 | Create Upload button on summary sheet(Low priorty) | Create a upload button on summary sheet for upload that paricular workbook on for siteID ( it will reduce 3 to 4 steps for uploading ) ON LOW PRIORITY

## goals
Goal
Reduce clinic spin addition flow from 6 days to 3 days
Reduce exchange iterations by
Eliminate all errors on identified fields for validations
Easy to use

## User-Story
Task Name | Description | Estimatedtime | ToDO | Activity | Question
SPIKE: Atomic validators for indivisual worksheets | for atomic validators for email,number and regular expression
Validators for individual worksheets/forms
Summary sheet | it shows all sheet validation summary,which is show after valdating different sheets.
Hardware_Network Details | it contain information regarding hardware and network related to run the DocuTAP software.
Practice Questionnaire | this sheet contain all clinic details
HL7 Interfaces(Exchange of info between medical applications) | DocuTAP is able to interface and exchange data with HL7-compliant equipment with some mandatory fields.
Contracted for conversions of data from an existing system | Data Conversion for Vendaor details with mandatory field validator
DocuTAP to create user logins | This sheet contain douctap user login information with mandatory field validator
Provider Information | This sheet is contain Provider information with some mandatory validator fields
Provider signature. | it contains provider digital signature for with mandatory field validator.
Insurance Companies Details. | DocuTAp Insurance companies form some of the fields are mandatory field
Insurance (Payer) Contracts Details | it is a copy of your signed contracts to your billing company.
Standard Clinic Fees strucutre | it’s a clinic fees structure and some fields are mandatory
Cash Payement Details | Cash pay fields with mandatory validators
Retail Medications/Items for selling | if clinic plans to sell Medical Equipment or Medications so there are some fields which is mandatory to fill
In-house Lab report | it’s a clinic in house lab report, which contain doctor details and related to report details.
Statement Configuration | DocuTAP reps will auto-generate your statements daily with a balance is greater than $5
Billing details (Collections Set Up Information) | It contain Billing details for patients through a collection agancy
Billing agreement (Collection Letter Content) | agreement of billing, its contain terms and condition of Billinf mode.
Letters/Forms wapper | its contain list of letter or documents which will provide by clinic
Referring & Primary Care Providers -- Can be input by Facility | it contain primary details information
Validators sheet for turnOn/turnOff | its shows all validators for sheet/cell/field level and on the basis of you can turn it ON/OFF.
Developer sheet | its degine for developer, he can manage all function details accordinally worksheet/cells. It should be protected mode and not visibal.
Webservice for copying/stream/feeding documents from disc/DFS/NAS | The website should invoke a webservice to upload or fetch documents from disc. The file location will be behind a firewall hence not directly accessible to the Webserver. The webservice needs to be setup to have permissions to access files on the disc.
Filenaming convention | Come up with a filename convention to avoid conflicts. Suggested parameters: Clinic name, date of transaction, GUID
SPIKE: List of all combinational validators | Applying combinational validation across the sheets, if it required and auto fill.
Combination validator for sheet1(Validation Summary) | Applying Combinational Validation for validation summary on first sheet, shows all validation errors in that sheet
Combination validator for sheet20(Validator sheet) | Applying Combinational validation for validator sheet for turn on /turn off facility provide by sheet/cell level.
Combination validator for sheet21(Devloper sheet) | Applying Combinational validation for showing all function name in one place which is helpful for developers only.
Spike - turn on and turn off validators/field
Impliment - Ability to turn on and turn off validators/field | OTL generate a link which will be uniquely for clinic and it contain file name and one time clickable
One time link (OTL) for providing Clinic template
Website link generation for DocuTAP implementation team
Generate a single useable link for download | DocuTAP's clinic implementation team should be able to generate a single use link for download
One time link (OTL) for providing Clinic template | This link generates a link that provides to the Clinic representative with a one time downloadable Excel file (template)
OTL for sending updated/reviewed Clinic details XLS file | A DocuTAP representative might edit an XLS file, then set this file as the downloadable Excel file for the OTL
OTL for uploading an XLS file with filled in Clinic details | A Clinic representative should be able to upload a validated XLS file using an OTL
Uploading xls file | Upload the excel file with a good GUI and appropiat message.
Validating for each excel worksheet. | On a server side valdation
Verify and uploaded XLS file
Varify all excel file check th | Once a clinic representative uploads a Clinic details file as an XLS file verify that it is a file that is a valid input for the Data Uploader application
SPIKE: Auto fill details fields
Implimentation of Auto filled details in | Auto filled functionality is like when you entered on first sheet name then rest of name auto fill by across the sheet.
Notification for state changes
Spike - Sending Notification | R&D for sending Notification
Implimentation of Notification for state changes. | Notification send from both DocuTAp represntative as well as clinic reps and Clinic reps EID would taken from UI not configrable
Store details for Clinic and DocuTAP reps/Clinic | Store a sheet in common place for Acknowledge the Clinic represntative
Generate unique tracking number for each Clinic | Generate a unique tracking number for each clinic which contain file path and file name
Enforce HTTPS | Applying https link for security point of view.

## Task
Sprints (Minimal End to End project) * validation work only one cell for each sheet.
Story | Description | Estimatedtime | TODO | Activity
SPIKE: Atomic validators for indivisual worksheets | for atomic validators for email,number and regular expression | 8Hrs
Spike: validate buton impliment in a sheet | Add a validate buton on every sheet to validate the mandatory fields | 8Hrs
Summary sheet | it shows all sheet validation summary,which is show after valdating different sheets. It will show only one cell error message | 4 Hrs
Hardware_Network Details | it contain information regarding hardware and network related to run the DocuTAP software. | 4 Hrs
Practice Questionnaire | this sheet contain all clinic details | 4 Hrs
HL7 Interfaces(Exchange of info between medical applications) | DocuTAP is able to interface and exchange data with HL7-compliant equipment with some mandatory fields. | 4 Hrs
Contracted for conversions of data from an existing system | Data Conversion for Vendaor details with mandatory field validator | 4 Hrs
DocuTAP to create user logins | This sheet contain douctap user login information with mandatory field validator | 4 Hrs
Provider Information | This sheet is contain Provider information with some mandatory validator fields | 4 Hrs
Provider signature. | it contains provider digital signature for with mandatory field validator. | 4 Hrs
Insurance Companies Details. | DocuTAp Insurance companies form some of the fields are mandatory field | 4 Hrs
Insurance (Payer) Contracts Details | it is a copy of your signed contracts to your billing company. | 4 Hrs
Standard Clinic Fees strucutre | it’s a clinic fees structure and some fields are mandatory | 4 Hrs
Cash Payement Details | Cash pay fields with mandatory validators | 4 Hrs
Retail Medications/Items for selling | if clinic plans to sell Medical Equipment or Medications so there are some fields which is mandatory to fill | 4 Hrs
In-house Lab report | it’s a clinic in house lab report, which contain doctor details and related to report details. | 4 Hrs
Statement Configuration | DocuTAP reps will auto-generate your statements daily with a balance is greater than $5 | 4 Hrs
Billing details (Collections Set Up Information) | It contain Billing details for patients through a collection agancy | 4 Hrs
Billing agreement (Collection Letter Content) | agreement of billing, its contain terms and condition of Billinf mode. | 4 Hrs
Letters/Forms wapper | its contain list of letter or documents which will provide by clinic | 4 Hrs
Referring & Primary Care Providers -- Can be input by Facility | it contain primary details information | 4 Hrs
Validators sheet for turnOn/turnOff | its shows all validators for sheet/cell/field level and on the basis of you can turn it ON/OFF. | 4 Hrs
Developer sheet | its degine for developer, he can manage all function details accordinally worksheet/cells. It should be protected mode and not visibal. | 4 Hrs
Webservice for copying/stream/feeding documents from disc/DFS/NAS | The website should invoke a webservice to upload or fetch documents from disc. The file location will be behind a firewall hence not directly accessible to the Webserver. The webservice needs to be setup to have permissions to access files on the disc. | TBD
Filenaming convention | Come up with a filename convention to avoid conflicts. Suggested parameters: Clinic name, date of transaction, GUID | TBD
Spike : Combinational validator for different sheet | Applying Combinational validator for filling different sheets. | 8Hrs.
Impliment Combinational validator in all sheets. |  | 8Hrs.
Spike:Ability to turn on and turn off validators/field | Applying like turn ON/turn OFF functionality in the sheets. | 4 Hrs
Implimentation of turn ON/OFF | Impliment of turn ON/turnOFF functionality in validator sheets | 8Hrs
Create a GUI for template Downloadable link. | Setup enviourment and create GUI for template downloading with a good naming convention URL | 8Hrs
One time link (OTL) for providing Clinic template | DocTAP will generate a link which contains | 8Hrs
validate the sheet from server side | work book to validate from serverside for all exjisting sheet of mandatory fileds. | 8Hrs
OTL for uploading an XLS file with filled in Clinic details | Create a GUI page using upload control. | 8Hrs
Impliments uploading functionality and validate of appropriate excel sheet. | Impliment all uploade functionality and validate from server side and check file extension as well as mandatory fileds | 8Hrs
SPIKE: Auto fill details fields | Reasearch the auto fill functionality from another sheet | 8Hrs
Impliment auto fill functionality across the sheet | Auto fill functionality impliment in all sheets where as we required to populate the cell value. | 8Hrs
Sending Notification for state change | Notification GUI degine and validate client side | 8Hrs
imlimentation of Notification for both side | Send notification to Docutap reps as well as clinic representative | 8Hrs
Store details for Clinic and DocuTAP reps/Clinic | Store excel work book for future Acknowledgement. | 8hrs
Generate unique tracking number for each Clinic | Generate Unique tracking No for every clinic | 8hrs
Enforce HTTPS | Impliment HTTPS security | 8Hrs

## MVPRC1
User story No | Task ID | Task Name | Est. Hrs | Todo | Actual | Start Date | End date | Status
1 | 1 | SPIKE: Atomic validators for indivisual worksheets | 4 | 4
1 | 2 | Spike : Numeric checks, Email,Alphnumeric checks in a worksheet | 4 | 4
2 | 1 | Spike : Combinational validator | 8 | 0
2 | 2 | Implimentation of combinational validation in per sheet (18 Sheets) | 4 | 0
3 | 1 | Single cell validation for each sheet with ActiveX control button | 8 | 0
3 | 2 | Add Summary validation sheet for showing all validation summary | 8 | 0
3 | 3 | Add Developer sheet for maintaining Funtion name corrusponding to worksheet/cell/fields | 8 | 0
4 | 1 | Spike : turn on/turn off functionality in a excel sheet | 4 | 0
4 | 2 | Add Turn On/turn Off functionality in Validator sheet | 8 | 0
5 | 1 | Create GUI For wesite link generation | 4 | 0
5 | 2 | Implimentation of Website link generation in a .Net framework | 8 | 0
6 | 1 | One time link Generate for Clinic template | 4 | 0
6 | 2 | Make it Downloadable file for indivisual Clinic (it maintain uniqueness for each clinic) | 8 | 0
7 | 1 | Sending Updated and reviewd clinic data | 8 | 0
8 | 1 | Create GUI for Uploading and Impliment logic | 8 | 0
9 | 1 | Varify the file name and validate from Server side on Excel | 8 | 0
10 | 1 | Create a WCF Service to communicate to store & fetching | 8 | 0
10 | 2 | Implimentation and Hosting of Service in the server | 8 | 0
11 | 1 | Filenaming convention | 0 | 0
12 | 1 | Spike : Auto fill cell value in different sheet and different cells | 8 | 0
12 | 2 | Implimantation of Auto fill value in the sheet | 8 | 0
13 | 1 | Create GUI for Notification create Model structure because Clinic representative EID get from UI | 8 | 0
13 | 2 | Implimenatation of Notification to DocuTAp and Clinic repsentative. | 8 | 0
14 | 1 | For Storing data on server side | 8 | 0
16 | 1 | Make it as HTTPs form | 8 | 0

## MVPRC1-05.05.2014
User story No | Task ID | Task Name | Est. Hrs | Todo | Actual | Start Date | End date | Status
1 | 1 | SPIKE: Atomic validators for indivisual worksheets | 4 | 4 |  | 24.04.2014 | 24.04.2014 | Done
1 | 2 | Spike : Numeric checks, Email,Alphnumeric checks in a worksheet | 4 | 4 |  | 24.04.2014 | 24.04.2014 | Done
2 | 1 | Spike : Combinational validator | 4 | 0 |  | 25.04.2014 | 25.04.2014 | Done
2 | 2 | Implimentation of combinational validation in per sheet (18 Sheets) | 4 | 0 |  | 25.04.2014 | 25.04.2014 | Done
3 | 1 | Single cell validation for each sheet with ActiveX control button | 4 | 0 |  | 29.04.2014 | 29.04.2014 | Done
3 | 2 | Add Summary validation sheet for showing all validation summary | 4 | 0 |  | 29.04.2014 | 29.04.2014 | Done
3 | 3 | Add Developer sheet for maintaining Funtion name corrusponding to worksheet/cell/fields | 4 | 0 |  | 30.04.2014 | 30.04.2014 | Done
4 | 1 | Spike : turn on/turn off functionality in a excel sheet | 4 | 0 |  | 30.04.2014 | 30.04.2014 | Done
4 | 2 | Add Turn On/turn Off functionality in Validator sheet | 8 | 0 |  | 02.05.2014 | 02.05.2014 | Done
5 | 1 | Create a GUI for website mapping and added with Project | 8 | 0 |  | 05.05.2014 | 05.05.2014 | Done
5 | 2 | mapping and link with Clinic id specific account for DocuTAP representative | 8 | 0 |  | 06.05.2014 | 06.05.2014 | Done
6 | 1 | Create Expire Gui and once you hit the link after that it will expire only one time clickable. | 8 | 0 |  | 07.05.2014 | 07.05.2014 | Pending
7 | 1 | Create a GUI for selecting site and uploading the file and validate from server side. | 8 | 0 |  | 08.05.2014 | 08.05.2014 | Done
7 | 2 | Docutap representative can upload the worksheet(Template)on the basis of siteid | 8 | 0 |  | 09.05.2014 | 09.05.2014 | Done
7 | 3 | Docutap file store on disk with each file directory.. | 8 | 0 | 4 | 12.05.2014 | 12.05.2014 | Done
8 | 1 | Spike: Disable macro of exjisting sheet and copy and paste macro | 8 | 0 |  | 13.05.2014 | 13.05.2014 | Done
9 | 1 | Error handling for client side | 4 | 0 |  | 14.05.2014 | 14.05.2014 | Pending
9 | 2 | Error handling for Server side | 4 | 0 |  | 14.05.2014 | 14.05.2014 | Pending
10 | 1 | Create GUI for excel uploading from clinic representative and validate on client and server side | 4 | 0 | 4 | 15.05.2014 | 15.05.2014 | Done
10 | 2 | Impliment validation and remove the exjisting macro and copy and paste Template macros(striping Macro) | 8 | 0
10 | 3 | Save file into disk space | 4 | 0 | 2 | 14.05.2014 | 14.05.2014 | Done
11 | 1 | Make it Downloadable file for indivisual Clinic (it maintain uniqueness for each clinic) | 8 | 0 | 5 | 14.05.2014 | 15.05.2014 | Done
12 | 1 | Notify to DocuTAp and Clinic repsentative. | 8 | 0 | 4 | 15.05.2014 | 15.05.2014 | Done
12 | 2 | Implimenatation of Notification to DocuTAp and Clinic repsentative.on the success and failure Condition | 8 | 0 | 5 | 16.05.2014 | 16.05.2014 | Inprogress
13 | 1 | This link generates a link that provides the Clinic representative with a downloadable Excel file (template) | 8 | 0 |  | 23.05.2014 | 23.05.2014 | Done
13 | 2 | Associate a unique Site ID for Uploading | 8 | 0
14 | 1 | Create a WCF Service to communicate to store & fetching | 8 | 0 |  | 20.05.2014 | 20.05.2014 | Done
14 | 2 | Implimentation and Hosting of Service in the server | 4 | 0 |  | 21.05.2014 | 21.05.2014 | Done
15 | 1 | Filenaming convention | 0 | 0
16 | 1 | Spike : Auto fill cell value in different sheet and different cells | 8 | 0
16 | 2 | Implimantation of Auto fill value in the sheet | 8 | 0
17 | 1 | Create GUI for Notification create Model structure because Clinic representative EID get from UI | 4 | 0
18 | 1 | For Storing data on server side | 8 | 0 |  | 19.05.2014 | 19.05.2014
18 | 2 | For Storing data on server side data | 8 | 0
18 | 1 | Make it as HTTPs form | 8 | 0
27

## To_be_Completed_for MVP_by28May
User story No | Task ID | Task Name | Est. Hrs | Todo | Actual | Start Date | End date | Resource | Status
1 | 1 | SPIKE: Atomic validators for indivisual worksheets | 4 | 4 |  | 24.04.2014 | 24.04.2014 |  | Done
1 | 2 | Spike : Numeric checks, Email,Alphnumeric checks in a worksheet | 4 | 4 |  | 24.04.2014 | 24.04.2014 |  | Done
2 | 1 | Spike : Combinational validator | 4 | 0 |  | 25.04.2014 | 25.04.2014 |  | Done
2 | 2 | Implimentation of combinational validation in per sheet (18 Sheets) | 4 | 0 |  | 25.04.2014 | 25.04.2014 |  | Done
3 | 1 | Single cell validation for each sheet with ActiveX control button | 4 | 0 |  | 29.04.2014 | 29.04.2014 |  | Done
3 | 2 | Add Summary validation sheet for showing all validation summary | 4 | 0 |  | 29.04.2014 | 29.04.2014 |  | Done
3 | 3 | Add Developer sheet for maintaining Funtion name corrusponding to worksheet/cell/fields | 4 | 0 |  | 30.04.2014 | 30.04.2014 |  | Done
4 | 1 | Spike : turn on/turn off functionality in a excel sheet | 4 | 0 |  | 30.04.2014 | 30.04.2014 |  | Done
4 | 2 | Add Turn On/turn Off functionality in Validator sheet | 8 | 0 |  | 02.05.2014 | 02.05.2014 |  | Done
5 | 1 | Create a GUI for website mapping and added with Project | 8 | 0 |  | 05.05.2014 | 05.05.2014 |  | Done
5 | 2 | mapping and link with Clinic id specific account for DocuTAP representative | 8 | 0 |  | 06.05.2014 | 06.05.2014 |  | Done
7 | 1 | Create a GUI for selecting site and uploading the file and validate from server side. | 8 | 0 |  | 08.05.2014 | 08.05.2014 |  | Done
7 | 2 | Docutap representative can upload the worksheet(Template)on the basis of siteid | 8 | 0 |  | 09.05.2014 | 09.05.2014 |  | Done
7 | 3 | Docutap file store on disk with each file directory.. | 8 | 0 | 4 | 12.05.2014 | 12.05.2014 |  | Done
8 | 1 | Spike: Disable macro of exjisting sheet and copy and paste macro | 8 | 0 |  | 13.05.2014 | 13.05.2014 |  | Done
9 | 1 | Error Handling for client side like, Allowing only Xls file to upload | 8 | 0 |  |  |  |  | Pending
9 | 2 | Error handling for Server side like a. File Not Found b. Identifying irrelevant File. c. content length should exists | 8 | 0 |  |  |  |  | Pending
10 | 1 | Create GUI for excel uploading from clinic representative and validate on client and server side | 4 | 0 | 4 | 15.05.2014 | 15.05.2014 |  | Done
10 | 3 | Save file into disk space | 4 | 0 | 2 | 14.05.2014 | 14.05.2014 |  | Done
11 | 1 | Make it Downloadable file for indivisual Clinic (it maintain uniqueness for each clinic) | 8 | 0 | 5 | 14.05.2014 | 15.05.2014 |  | Done
12 | 1 | Notify to DocuTAp and Clinic repsentative. | 8 | 0 | 4 | 15.05.2014 | 15.05.2014 |  | Done
12 | 2 | Implemenatation of Notification (using smtp server) to DocuTap and Clinic repsentative.on the success and failure Condition. | 8 | 0 |  |  |  | Pradeep | Pending
13 | 1 | This link generates a link that provides the Clinic representative with a downloadable Excel file (template) | 8 | 0 |  | 23.05.2014 | 23.05.2014 |  | Done
13 | 2 | Associate a unique Site ID for Uploading on ever document Upload |  | 0
14 | 1 | Create a WCF Service to communicate to store & fetching | 8 | 0 |  | 20.05.2014 | 20.05.2014 |  | Done
14 | 2 | Implimentation and Hosting of Service in the server | 4 | 0 |  | 21.05.2014 | 21.05.2014 |  | Done
|  | A. Idenfity if a site Id is Unique | 8
a1 . Read the text file for all SiteIds and get the exists or not exists
|  | B. Ensure that Site Id is Unique for every docuTap upload | 8
| 3 | Read data from existing text file and Configuration mail id for Send Notification | [6 empty] | Pending
|  | a. Read the txt File and get all 2nd and 3rd columns | 5
|  | b. Get To and From Ids from text file | 4
| 4 | Maintain Configurable address for Saving Excel sheet | 8 | [5 empty] | Pending
| 5 | Make a One time clickable link for Clinic representative | 8 |  |  |  |  | Pradeep | Pending
| 6 | Server Side Validation Required for Upload only excel file | 4 | [5 empty] | Pending
48